## Tasks
Task | Assignee | Status | Due date | Status
Restructure TeX file into chapters |  | Cancled |  | It's not too long, just leave it as one document
Convert to knitr | Melissa | DONE | 2014-07-09
Write R functions for SIR algorithm + verify same as MCMC |  | Cancel this |  | Abandoned
Explore Hybrid arguments | Cole | DONE |  | Also added to run function
Writeup Hybrid algorithm | Cole | DONE
Writeup tuning guidance | Cole | zero
Writeup MCMC basics | Peter | zero
Develop difficult posterior example model | Cole | DONE |  | Used logistic
document -mcr to restart a chain | Peter
Clean up snakes and its R plot code for submission into r2admb | Cole | On pause | 2014-07-18 | Ben liked the idea of merging it into his package. Delaying until further decisions are made.
Cleanup pairs.admb function | Cole | DONE
Clean up run.mcmc function | Cole | DONE
Check with Ianelli about authorship issues | Cole | DONE |  | Got the green light, authorship is ours
Migrate the guide to Github (after Spring quarter) | Cole | DONE
Investigate other R packages for similar functionality | Cole | DONE |  | R2admb (Ben Bolker) has some overlap, I propose we try to merge our functions in there
Describe the hst output file | Melissa |  | 2014-07-18
Create list of proposed changes to the source code | Cole | started |  | See next sheet
Expand possible areas for trouble-shooting help: non posdef, no sd.report variables, bounds issues | Melissa
What is option -mcec? What is empirical covariance? | Cole | DONE |  | commented out; presumably similar to supplying user covariance from partial chain
Mention capabilities of R2admb
define what mcmult argument does
Writeup the mcprobe algorithm to go with the plots

## Proposed updates
Concurrent to the guide I think we should propose some changes to the source code that will improve the user's experience with ADMB
I usually grep the source code I'm looking for, then lookup that file on the website. Line #'s are added with #l<number> tacked on to the end of the URL
Change | Source code location
Set mceval default to 1, instead of blank -- nothing is saved in this case | http://admb-project.org/documentation/api/xxmcmc_8cpp_source.html#l00521
Expand the info in the hst file (mcmc options used, time started; ended | http://admb-project.org/documentation/api/xxmcmc_8cpp_source.html#l01021
Remove need for an sdreport variable for MCMC | http://www.admb-project.org/documentation/api/xxmcmc_8cpp_source.html#l00147
Use a random seed if none is provided by user
Give more informative output during hybrid runs | http://admb-project.org/documentation/api/hybmcmc_8cpp_source.html#l00086
Questions for Dave:
Why need sdreport variable for MCMC? | Not needed; remove this in future versions
What is the difference between bounding functions? | Not really sure; perhaps suggest this be renamed to bounded_flag since it has nothing to do with the hybrid method.