## Tasks
Task | Assignee | Status | Due date | Status
Restructure TeX file into chapters
Convert to knitr | Melissa | zero | 2014-07-09
Write R functions for SIR algorithm + verify same as MCMC |  | Cancel this
Explore Hybrid arguments | Cole | 1/2 done
Writeup Hybrid algorithm | Cole | zero
Writeup tuning guidance | Cole | zero
Writeup MCMC basics | Peter | zero
Develop difficult posterior example model | Cole
document -mcr to restart a chain from hst file | Peter
Clean up snakes and its R plot code for submission into r2admb | Melissa |  | 2014-07-18
Cleanup pairs.admb function | Cole | 75% done
Clean up run.mcmc function | Cole
Check with Ianelli about authorship issues | Cole |  |  | Got the green light, authorship is ours
Migrate the guide to Github (after Spring quarter) | Cole
Investigate other R packages for similar functionality | Cole |  |  | R2admb (Ben Bolker) has some overlap, I propose we try to merge our functions in there
Describe the hst output file | Melissa |  | 2014-07-18
Create list of proposed changes to the source code
Expand possible areas for trouble-shooting help: non posdef, no sd.report variables, bounds issues
What is option -mcec? What is empirical covariance?
What is the .bgs file used for? Read in if mcmc2_flag==TRUE
Deduce which options are available for the hybrid method

## Proposed updates
Concurrent to the guide I think we should propose some changes to the source code that will improve the user's experience with ADMB
I usually grep the source code I'm looking for, then lookup that file on the website. Line #'s are added with #l<number> tacked on to the end of the URL
Change | Source code location
Set mceval default to 1, instead of blank -- nothing is saved in this case | http://admb-project.org/documentation/api/xxmcmc_8cpp_source.html#l00521
Expand the info in the hst file (mcmc options used, time started; ended | http://admb-project.org/documentation/api/xxmcmc_8cpp_source.html#l01021
Remove need for an sdreport variable for MCMC | http://www.admb-project.org/documentation/api/xxmcmc_8cpp_source.html#l00147
Use a random seed if none is provided by user
Questions for Dave:
Why need sdreport variable for MCMC?
What is the difference between bounding functions?