## Tasks
Task | Assignee | Status | Due date | Status
Restructure TeX file into chapters |  | Cancled |  | It's not too long, just leave it as one document
Convert to knitr | Melissa | DONE | 2014-07-09
Write R functions for SIR algorithm + verify same as MCMC |  | Cancel this |  | Abandoned
Explore Hybrid arguments | Cole | DONE |  | Also added to run function
Writeup Hybrid algorithm | Cole | DONE
Writeup tuning guidance | Cole | DONE
Writeup MCMC basics | Peter | DONE
Develop difficult posterior example model | Cole | DONE |  | Used logistic
document -mcr to restart a chain | Peter
Clean up snakes and its R plot code for submission into r2admb | Cole | On pause | 2014-07-18 | Ben liked the idea of merging it into his package. Delaying until further decisions are made.
Cleanup pairs.admb function | Cole | DONE
Clean up run.mcmc function | Cole | DONE
Check with Ianelli about authorship issues | Cole | DONE |  | Got the green light, authorship is ours
Migrate the guide to Github (after Spring quarter) | Cole | DONE
Investigate other R packages for similar functionality | Cole | DONE |  | R2admb (Ben Bolker) has some overlap, I propose we try to merge our functions in there
Describe the hst output file | Melissa | DONE | 2014-07-18
Create list of proposed changes to the source code | Cole | 50% |  | See next sheet; will adapt this from feedback from the ADMB developers
Expand possible areas for trouble-shooting help: non posdef, no sd.report variables, bounds issues | Melissa
What is option -mcec? What is empirical covariance? | Cole | DONE |  | commented out; presumably similar to supplying user covariance from partial chain
Mention capabilities of R2admb | ?

## Proposed updates
Concurrent to the guide I think we should propose some changes to the source code that will improve the user's experience with ADMB
I usually grep the source code I'm looking for, then lookup that file on the website. Line #'s are added with #l<number> tacked on to the end of the URL
Change | Source code location
Set mceval default to 1, instead of blank -- nothing is saved in this case | http://admb-project.org/documentation/api/xxmcmc_8cpp_source.html#l00521
Expand the info in the hst file (mcmc options used, time started; ended | http://admb-project.org/documentation/api/xxmcmc_8cpp_source.html#l01021 | I totally agree with these, maybe add a section to the hst file called MCMC stats. I also think adding the ability to write the unscaled hist values, or maybe even each saved value, to a binary file (similar to the psv file) would be really helpful so that users can read in their saved param values from one file and their saved sdreport values from another. Of course the user can do it with an IO object, but I bet writing it to a binary file is hella faster - Melissa
Remove need for an sdreport variable for MCMC | http://www.admb-project.org/documentation/api/xxmcmc_8cpp_source.html#l00147
Use a random seed if none is provided by user
Give more informative output during hybrid runs | http://admb-project.org/documentation/api/hybmcmc_8cpp_source.html#l00086
More informative output for MCMC, especially the -objective fn value (llc) | http://admb-project.org/documentation/api/xxmcmc_8cpp_source.html#l00627
Questions for Dave:
Why need sdreport variable for MCMC? | Not needed; remove this in future versions
What is the difference between bounding functions? | Not really sure; perhaps suggest this be renamed to bounded_flag since it has nothing to do with the hybrid method.